## NIST CSF 2.0 Risk Register
Risk ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Risk Score | Current Controls | Recommended Treatment | Owner | Target Date
R-001 | No formal threat intelligence subscription; reliance on vendor alerts only | Identify | 3 | 3 | 9 | Ad-hoc vendor security alerts monitored by IT team | Subscribe to formal threat intelligence feed (e.g., FS-ISAC) for proactive monitoring | CISO | Q3 2026
R-002 | Encryption at rest not applied to all data stores, including document imaging archive | Protect | 2 | 4 | 8 | Encryption in transit implemented across all internal web pathways | Deploy full disk and database-level encryption at rest across all document storage repositories | IT Director | Q3 2026
R-003 | Loan origination vendor has not provided a current SOC 2 Type II report | Govern (Supply Chain Risk) | 3 | 4 | 12 | Initial vendor security assessment questionnaire performed at onboarding | Formalize vendor oversight process with mandatory SOC 2 collection and escalation criteria | VP, Vendor Risk Mgmt | Q3 2026
R-004 | Incident response plan not tested via tabletop exercise within the last 18 months | Respond | 3 | 3 | 9 | Documented Incident Response Plan reviewed annually by CISO | Schedule and execute a structured tabletop testing simulation with key business leaders | CISO | Q4 2026
R-005 | Cyber risk appetite and supply chain risk oversight not formally documented for board reporting | Govern | 2 | 3 | 6 | Quarterly high-level GRC updates provided to Board Risk Committee | Draft and formalize explicit corporate cyber risk appetite statements for Board approval | Chief Risk Officer | Q4 2026
R-006 | Recovery time objectives not formally documented and recovery not tested end-to-end for critical systems | Recover | 3 | 4 | 12 | Nightly standard file-level data backups executed and stored offsite | Document explicit RTO metrics and conduct full end-to-end technical disaster recovery tests | IT Director | Q1 2027
R-007 | Annual vendor risk questionnaires not consistently followed up with SOC report review | Govern (Supply Chain Risk) | 3 | 3 | 9 | Annual vendor risk questionnaire sent out to critical providers | Establish formal review workflow and tracking dashboard for all received third-party SOC reports | VP, Vendor Risk Mgmt | Q3 2026
R-008 | Lack of formalized periodic access recertifications for administrative and privileged users | Access Management | 3 | 4 | 12 | Manager approval required during initial onboarding access setup | Implement formalized quarterly user access recertification campaigns driven by managers | CISO | Q4 2026
R-009 | Delayed patching cycles on non-critical servers creating potential vulnerability windows | Patch Management | 4 | 3 | 12 | Critical operating system security updates deployed within 30 days | Incorporate non-critical infrastructure into centralized vulnerability scanner schedules | IT Director | Q1 2027
R-010 | Employee security awareness training lacks specialized phishing simulations for high-target departments | Security Awareness | 3 | 3 | 9 | Annual generic compliance video training mandatory for all staff | Deploy targeted, high-frequency phishing simulations optimized for Finance/HR groups | CISO | Q4 2026
R-011 | Physical server room environmental monitoring lacks automated alerting for temperature fluctuations | Physical Security | 2 | 4 | 8 | Standard HVAC system checks conducted quarterly by building facilities | Install automated temperature and environmental sensor monitors with real-time SMS alerts | IT Director | Q2 2027
R-012 | Shared administrative accounts used across legacy local server environments | Access Management | 3 | 4 | 12 | Strong password complexity requirements enforced via Group Policy | Deprecate shared local admin credentials and roll out individual privileged access accounts | CISO | Q4 2026
R-013 | Critical patches for core banking terminals deployed manually due to lack of automated tooling | Patch Management | 3 | 4 | 12 | IT department manually tracks and applies server baseline hotfixes | Acquire and implement automated endpoint patch management system across all terminal pools | IT Director | Q1 2027
R-014 | New employees starting work prior to completing mandatory initial security awareness modules | Security Awareness | 4 | 2 | 8 | HR triggers training invitation email within 5 business days of hire | Enforce strict policy blocking active network logins until onboarding modules are completed | Chief Risk Officer | Q3 2026
R-015 | Unescorted visitor logs for corporate facility server backup spaces managed via paper only | Physical Security | 2 | 3 | 6 | Physical badge access required for entry to main building doors | Digitize facility visitor access tracking logs with mandatory dual-signature workflows | IT Director | Q2 2027